*Technicians/Time onsite:*

1. Cory Hale – 9hrs
2. Keith – 8hrs
3. Jesse – 8hrs
4. Matt – 6hrs

*Tasks Completed:*

1. Cable ran for stand alone training rooms 1523 and 1524 completed except for 2 cresnet cables to each location still need to be pulled
2. Cable ran to combination training room 1525 except for 2 dm cables still need to be pulled
3. RG 6 cables ran to each of the perimeter displays on the 15th floor
4. Missing perimeter display structure installed on 18th and 19th floors

*Tasks on the agenda for the next site visit:*

1. Complete cable pulls for combination training  rooms 1525 and 1527, stand alone training room 1528 and medium training room 1515
2. Run all antenna jumpers between the IDF closet and the UPS room
3. Run missing cresnet cables to stand alone room 1523 and 1524 and missing DM cables to combination room 1525

*Equipment/Tools required for next site visit:*

* 1. Drywall saw or 3 in hole saw to cut holes for sleeves
  2. Bandsaw to cut sleeves to size

*Issues with site conditions:*

1. Elevators being used to bring in deliveries all day making wait time long
2. Running cable at the same time as the data guys slowing down production

I am feeling good about being able to knock out the rest of the 15th floor tomorrow. If it doesn’t seem productive to have all of us working on those cable pulls I might get Keith and Matt working on the 16th floor display cables.